## Budget
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Construction Budget
Track estimated vs actual cost by work section — variance and % calculate automatically
Project | 4-bedroom bungalow (example) |  | Location | Lugbe, Abuja
Client | Mr & Mrs Adeyemi (example) |  | Contractor | Example Builders Ltd
Budget date | 2026-10-01
Work section | Estimated | Actual to date | Variance | Variance (%) | Notes
Substructure | 7722000 | 8030000 | 308000 | 3.989% | Extra excavation — soft soil at rear
Frame & walling | 10144000 | 9839000 | -305000 | -3.007% | Complete
Roofing & ceiling | 7768000 | 8700000 | 932000 | 12% | Roof timber price rose 15% since estimate
Doors & windows | 1212000 | 1212000 | 0 | 0% | Complete
Finishes | 6538000 |  |  |  | Not started
Services | 2774000 |  |  |  | Not started
External works (fence, gate, paving) | 4800000 |  |  |  | Phase 2
TOTAL | 40958000 | 27781000 | 935000
PROJECT TOTALS
Construction budget | 40958000
Contingency (%) | 10%
Contingency | 4095800
Professional fees (architect, QS, engineer) | 2500000
Approvals & permits | 650000
TOTAL PROJECT BUDGET | 48203800
Spent to date | 27781000
Remaining budget | 20422800
How to use: enter your own estimate per section in column B, and update "Actual to date" as you pay for materials and labour. A positive variance means you are over budget on that section.
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Building Cost Estimator at https://nigeriabuildingcost.ng/estimator