## Invoice
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Construction Invoice
Progress invoice with retention and VAT
Invoice no. |  | INV-2026-031
Invoice date |  | 2026-10-13
Bill to |  | Mr & Mrs Adeyemi (example)
Due date |  | 2026-10-27
Project |  | 4-bedroom bungalow, Lugbe, Abuja
Stage |  | Roof level (Stage 2 of 4)
# | Description | Qty | Unit | Rate | Amount
Labour
1 | Blockwork to lintel level — 9" and 6" walls | 3900 | blocks | 100 | 390000
2 | Concrete work to columns, lintels and ring beam | 13.7 | m³ | 22000 | 301400
3 | Iron bender (12 days) | 12 | days | 8000 | 96000
Materials
4 | 9" sandcrete blocks | 2400 | nr | 750 | 1800000
5 | 6" sandcrete blocks | 1500 | nr | 600 | 900000
6 | Cement (Dangote 42.5R) | 260 | bags | 14000 | 3640000
7 | Y12 and Y16 bars | 213 | lengths | 10200 | 2172600
Subcontractors & other
8 | Equipment hire — concrete mixer & vibrator | 6 | days | 25000 | 150000
|  |  |  | SUBTOTAL | 9450000
|  | Subtotal |  |  | 9450000
|  | Retention (%) |  |  | 5%
|  | Less retention |  |  | -472500
|  | VAT (%) |  |  | 7.5%
|  | VAT |  |  | 708750
|  | Less previous payments |  |  | -18500000
|  | AMOUNT DUE |  |  | -8813750
PAYMENT DETAILS
Bank |  | Your bank
Account name |  | Example Builders Ltd
Account no. |  | 0123456789
Reference |  | INV-2026-031
Retention is held by the client and released at the end of the defects liability period. Remove VAT if you are not VAT-registered.
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Invoice Generator at https://nigeriabuildingcost.ng/invoice