## Management plan
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Construction Management Plan
One page per topic: how the job will be run, who is responsible and what is still open
Project | 4-bedroom bungalow (example) | Location | Lugbe, Abuja
Client | Mr & Mrs Adeyemi (example) | Contractor | Example Builders Ltd
Project manager | Engr. (name) | Revision | Rev 1 — 13 Oct 2026
SCOPE & DOCUMENTS
Item | Plan / requirement | Responsible | Status
Approved drawings | Architectural, structural, M&E drawings — latest revision on site at all times | Architect | Done
Building permit | Development permit from AMMC/Development Control displayed on site board | Client | Done
Bill of Quantities | Priced BoQ agreed and signed with contract | QS | Done
SCHEDULE & REPORTING
Item | Plan / requirement | Responsible | Status
Programme | Gantt chart updated weekly; 20-week duration | Contractor | Ongoing
Daily site report | Weather, labour, work done, deliveries, issues — sent to client every evening | Site supervisor | Ongoing
Progress meeting | Fortnightly on site with client and consultants | PM | Ongoing
COST CONTROL
Item | Plan / requirement | Responsible | Status
Budget tracking | Actual vs estimate per section reviewed monthly | QS | Ongoing
Variations | No extra work without a signed variation order | PM | Ongoing
Valuations & payments | Stage payments against signed interim valuation; 5% retention | QS / client | Ongoing
PROCUREMENT
Item | Plan / requirement | Responsible | Status
Materials | Cement, blocks, rods ordered against BoQ with 3 supplier quotes for items over ₦500k | Contractor | Ongoing
Material testing | Block crushing test and concrete cube tests at 7 and 28 days | Engineer | Pending
Storage & security | Lockable store, cement on pallets off the ground, delivery log | Storekeeper | Done
HEALTH, SAFETY & ENVIRONMENT
Item | Plan / requirement | Responsible | Status
Site safety | PPE compulsory, toolbox talk every Monday, first aid box on site | HSE officer | Ongoing
Neighbours & traffic | Deliveries 8am–5pm only, road kept clear, dust damped in dry season | Supervisor | Ongoing
Waste | Debris cleared weekly by licensed waste contractor | Contractor | Ongoing
QUALITY
Item | Plan / requirement | Responsible | Status
Inspections | Engineer to inspect reinforcement before every concrete pour | Engineer | Ongoing
Snagging | Snag list walk-through 2 weeks before handover | PM | Pending
RISKS
Item | Plan / requirement | Responsible | Status
Rainy season | Plan substructure and roofing outside peak rains; tarpaulins on site | PM | Ongoing
Price increases | Buy rods and roofing early; 5% contingency in budget | QS | Ongoing
CONTACTS
Role | Name & company | Phone | Email
Client | Mr & Mrs Adeyemi (example) | 080x xxx xxxx
Architect
Structural engineer
Quantity surveyor
Contractor | Example Builders Ltd
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build (free project tracker) at https://nigeriabuildingcost.ng/construction-management-software-nigeria