## Proposal
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Construction Proposal
Your bid to a client — who you are, how you will do the job, the price and the timeline
Prepared for | Mr & Mrs Adeyemi (example)
Prepared by | Example Builders Ltd
Project | 4-bedroom bungalow, Lugbe, Abuja
Date | 2026-10-13
1. UNDERSTANDING OF THE PROJECT
Build a 4-bedroom en-suite bungalow of about 165m² on the client's plot in Lugbe, from foundation to handover, to the approved drawings. The client wants to move in before the end of Q1 2027 and needs clear monthly cost reporting while living abroad.
2. OUR APPROACH
• Weekly photo updates and a shared online progress log the client can check any time
• Materials bought against the BoQ; receipts shared for every major purchase
• Engineer inspection before every concrete pour; cube and block tests documented
• Fortnightly site meeting (in person or video call)
3. PRICE SUMMARY
Section | Basis | Amount
Substructure | As per BoQ | 9266000
Frame & walling | As per BoQ | 12172000
Roofing & ceiling | As per BoQ | 9321000
Doors & windows | As per BoQ | 1454000
Finishes | As per BoQ | 7845000
Services | As per BoQ | 3328000
| TOTAL (excl. VAT) | 43386000
4. TIMELINE
Phase | Duration | Payment due
Mobilisation & substructure | Weeks 1–5 | 40% on signing
Superstructure & roofing | Weeks 6–12 | 30% at roof level
Services & finishes | Weeks 12–18 | 25% at finishing
Snagging & handover | Weeks 19–20 | 5% retention after 6 months
5. WHY US
• 12 completed residential projects in Abuja since 2019 (list and references on request)
• COREN-registered engineer on staff
• All-risk insurance on site works
• 6-month defects liability period
6. VALIDITY & ACCEPTANCE
This proposal is valid for 30 days. Signing below confirms acceptance; a formal contract will follow.
For Example Builders Ltd | Client acceptance
Name: | Name:
Date: | Date:
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Quotation Generator at https://nigeriabuildingcost.ng/quotation