## Risk register
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Construction Risk Register
Score = likelihood × impact (1–5 each). 15+ = high, 8–14 = medium, below 8 = low
Project |  | 4-bedroom bungalow (example) |  | Location |  | Lugbe, Abuja
Client |  | Mr & Mrs Adeyemi (example) |  | Contractor |  | Example Builders Ltd
Owner |  | Project manager |  | Reviewed |  | 2026-10-13
# | Risk | Category | Likeli-hood | Impact | Score | Response / mitigation | Owner
1 | Building material prices rise mid-project (cement, rods, roofing) | Cost | 4 | 4 | 16 | Buy rods & roofing early; 5% contingency; price-validity clause in contract | QS
2 | Heavy rain delays substructure and roofing | Schedule | 4 | 3 | 12 | Programme substructure before peak rains; tarpaulins; drainage on site | PM
3 | Theft of materials from site | Cost | 3 | 3 | 9 | Night security, lockable store, delivery log, materials bought just-in-time | Supervisor
4 | Poor quality blocks / concrete | Quality | 3 | 5 | 15 | Block crushing tests; concrete cubes; reject sub-standard deliveries | Engineer
5 | Client payment delays | Cash flow | 3 | 4 | 12 | Stage payments tied to milestones; stop-work clause; cash-flow forecast | Contractor
6 | Development control stop-work order | Legal | 2 | 5 | 10 | Approved permit on site board; build exactly to approved drawings | Client
7 | Injury on site | Safety | 2 | 5 | 10 | HSE plan, PPE, toolbox talks, first aid trained staff | HSE officer
8 | Design change requested during construction | Scope | 3 | 3 | 9 | Variation order procedure; freeze design before roofing | PM

## Risk assessment
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Task Risk Assessment
Before each new activity: list the hazards, who could be hurt and the controls
Activity | Roof carcass & sheeting |  | Date |  | 2027-01-15
Assessed by | HSE officer |  | Workers involved |  | Carpenters (4), roofers (3)
Hazard | What could happen | Who is at risk | Likeli-hood | Impact | Score | Controls
Working at height | Fall from roof edge or through trusses | Carpenters, roofers | 3 | 5 | 15 | Scaffold at eaves; harness tied to ridge line; no work in rain or high wind
Lifting timber & sheets | Dropped load, back injury | Labourers | 3 | 3 | 9 | Rope & pulley; two-man lifts; exclusion zone below
Power tools | Cuts, electric shock | Carpenters | 2 | 3 | 6 | Tools checked daily; RCD; guards fitted
Sheet edges | Hand lacerations | Roofers | 3 | 2 | 6 | Cut-resistant gloves
Sun exposure | Heat stress, dehydration | All roof workers | 3 | 2 | 6 | Water breaks every hour; start at 7am
Assessed by |  |  | Briefed to workers by
Name: |  |  | Name:
Date: |  |  | Date:
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build at https://nigeriabuildingcost.ng/construction-management-software-nigeria