## Schedule & Gantt
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Construction Schedule & Gantt Chart
Change the start week or duration of any task and the bars move. Week 1 = the start date below.
Project |  | 4-bedroom bungalow (example) | [11 empty] | Location | [5 empty] | Lugbe, Abuja
Client |  | Mr & Mrs Adeyemi (example) | [11 empty] | Contractor | [5 empty] | Example Builders Ltd
Start date (week 1) |  | 2026-11-02 | [11 empty] | Target handover | [5 empty] | 2027-03-19
# | Task | Phase | Responsible | Start wk | Weeks | % done | After # | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
1 | Mobilisation, site clearance & setting out | Pre-construction | Contractor | 1 | 1 | 100% | — | █
2 | Excavation & foundation concrete | Substructure | Contractor | 2 | 2 | 100% | 1 |  | █ | █
3 | Foundation blockwork, filling & DPC | Substructure | Mason | 3 | 2 | 100% | 2 |  |  | █ | █
4 | German floor slab | Substructure | Contractor | 5 | 1 | 100% | 3 |  |  |  |  | █
5 | Blockwork to lintel level | Superstructure | Mason | 6 | 3 | 70% | 4 | [5 empty] | █ | █ | █
6 | Columns, lintels & ring beam | Superstructure | Iron bender / carpenter | 8 | 2 | 30% | 5 | [7 empty] | █ | █
7 | Gable walls & roof carcass | Roofing | Carpenter | 10 | 2 | 0% | 6 | [9 empty] | █ | █
8 | Roof covering, fascia & gutters | Roofing | Roofer | 12 | 1 | 0% | 7 | [11 empty] | █
9 | Electrical & plumbing first fix | Services | Electrician / plumber | 12 | 2 | 0% | 7 | [11 empty] | █ | █
10 | Plastering & screeding | Finishes | Plasterer | 13 | 3 | 0% | 9 | [12 empty] | █ | █ | █
11 | Windows & doors | Finishes | Aluminium installer | 15 | 1 | 0% | 10 | [14 empty] | █
12 | Ceiling | Finishes | Ceiling installer | 15 | 2 | 0% | 8 | [14 empty] | █ | █
13 | Floor & wall tiling | Finishes | Tiler | 16 | 2 | 0% | 10 | [15 empty] | █ | █
14 | Painting | Finishes | Painter | 17 | 2 | 0% | 13 | [16 empty] | █ | █
15 | Second fix — fittings, sockets, sanitary ware | Services | Electrician / plumber | 18 | 1 | 0% | 14 | [17 empty] | █
16 | Septic tank, soakaway & external drains | External works | Contractor | 14 | 2 | 0% | — | [13 empty] | █ | █
17 | Snagging, cleaning & handover | Close-out | Contractor / client | 19 | 1 | 0% | 15 | [18 empty] | █

## Milestones
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Milestone Chart
The checkpoints that matter to the client — and usually trigger a stage payment
# | Milestone | Planned date | Actual date | Status | Payment / notes
1 | Site handed over & setting out approved | 2026-11-06 | 2026-11-06 | Done | Mobilisation 40% paid
2 | Foundation & DPC complete (inspected) | 2026-12-04 | 2026-12-08 | Done | Development control inspection
3 | Lintel level reached | 2027-01-08 |  | On track
4 | Roof covered — building weather-tight | 2027-01-29 |  | At risk | Stage 2 payment 30%. Timber supply delayed
5 | Finishes complete | 2027-03-05 |  | On track | Stage 3 payment 25%
6 | Practical completion & handover | 2027-03-19 |  | On track | Retention 5% held for 6 months
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build (free project tracker) at https://nigeriabuildingcost.ng/construction-management-software-nigeria