## Scope of work
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Scope of Work
What is included, what is not, deliverables, timeline and payment milestones
Project |  | 4-bedroom bungalow (example) | Location | Lugbe, Abuja
Client |  | Mr & Mrs Adeyemi (example) | Contractor | Example Builders Ltd
Contract type |  | Lump sum, labour & materials
PROJECT SUMMARY
Construction of a 4-bedroom bungalow (all rooms en-suite + guest toilet), approx. 165m² floor area on a 15m × 30m plot, from site clearance to handover, in accordance with the approved drawings and the priced Bill of Quantities.
DELIVERABLES & TIMELINE
# | Deliverable | Includes | Start week | Weeks | % of contract | Status
1 | Substructure to DPC | Foundation, filling, DPM, floor slab | 1 | 5 | 18% | Done
2 | Superstructure | Blockwork, columns, lintels, ring beam | 6 | 4 | 22% | In progress
3 | Roofing | Roof timber, aluminium sheets, fascia, gutters | 10 | 3 | 12% | Not started
4 | Services | Electrical & plumbing installation, septic tank | 12 | 7 | 14% | Not started
5 | Finishes | Plaster, screed, tiles, ceiling, doors, windows, paint | 13 | 6 | 30% | Not started
6 | Handover | Snagging, cleaning, as-built drawings, keys | 19 | 1 | 4% | Not started
INCLUDED
• Supply of all materials and labour listed in the BoQ
• Site security and storage during construction
• Removal of construction debris
• Setting out and levels as per survey plan
EXCLUDED (CLIENT TO PROVIDE OR PRICE SEPARATELY)
• Fence, gate and external paving
• Borehole, overhead tank and pumping machine
• Generator, inverter or solar system
• Kitchen cabinets, wardrobes and furniture
• Statutory approvals and utility connection fees (AEDC meter, etc.)
ASSUMPTIONS
• Soil is normal (no rock, no high water table); special foundations will be a variation
• Client supplies water and electricity on site, or pays for tanker water/generator fuel
• Drawings will not change after contract signing without a variation order
Contractor |  |  | Client
Name: |  |  | Name:
Date: |  |  | Date:
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Quotation Generator at https://nigeriabuildingcost.ng/quotation