## Submittal log
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Construction Submittal Log
Samples, shop drawings and product data sent for approval before ordering or installing
Project |  | 4-bedroom bungalow (example) |  | Location |  | Lugbe, Abuja
Client |  | Mr & Mrs Adeyemi (example) |  | Contractor |  | Example Builders Ltd
Approver |  | Project architect / engineer
No. | Item submitted | Type | Spec section / BoQ ref | Submitted | Returned | Status | Rev.
S-01 | 9" sandcrete block — crushing test results | Test result | BoQ 2A | 2026-10-02 | 2026-10-05 | Approved | 0
S-02 | 0.55mm aluminium roofing sheet — colour sample (brick red) | Sample | BoQ 3B | 2026-10-06 | 2026-10-09 | Approved as noted | 0
S-03 | Roof truss layout drawing | Shop drawing | BoQ 3A | 2026-10-08 | 2026-10-12 | Revise & resubmit | 1
S-04 | 600×600 porcelain floor tile | Sample | BoQ 5C | 2026-10-12 |  | Pending | 0
S-05 | Concrete cube tests (7-day) — ring beam | Test result | BoQ 2D | 2026-10-13 |  | Pending | 0
Do not order or install anything marked "Pending", "Revise & resubmit" or "Rejected".
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build at https://nigeriabuildingcost.ng/construction-management-software-nigeria