## Daily site report
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Daily Site Report
One sheet per day — copy the tab for each new day
Date | 2026-10-13 | Report no. |  | 54
Project | 4-bedroom bungalow (example) | Location |  | Lugbe, Abuja
Client | Mr & Mrs Adeyemi (example) | Contractor |  | Example Builders Ltd
Supervisor | (name) | Hours worked |  | 7:30am – 5:00pm
WEATHER
Time | Condition | Temp (°C) | Work stopped? | Notes
Morning | Cloudy | 26 | No
Afternoon | Heavy rain | 24 | Yes | Rain 1:30–3:00pm; concrete pour moved to tomorrow
LABOUR ON SITE
Trade | Company / gang | Workers | Hours | Work done
Masons | Own gang | 4 | 8 | Blockwork to lintel level — bedrooms 3 & 4
Labourers | Own gang | 6 | 8 | Mixing mortar, carrying blocks
Iron benders | Subcontractor | 2 | 6 | Cut and bent lintel reinforcement
Carpenters | Subcontractor | 2 | 6 | Lintel formwork, living room
| Total workers | 14
MATERIALS DELIVERED
Material | Supplier | Qty | Unit | Received by / condition
Cement (Dangote) | Supplier A | 60 | bags | Storekeeper — good, stored on pallets
9" blocks | Block industry, Lugbe | 1000 | nr | 14 broken, noted on waybill
EQUIPMENT ON SITE
Equipment | Owned / hired | Hours used | Condition | Notes
Concrete mixer (1 bag) | Hired | 0 | Good | Idle — rain
Poker vibrator | Owned | 0 | Needs repair | Sent for repair
VISITORS & INSPECTIONS
Name | Organisation | Time in | Time out | Purpose
(Name) | Structural engineer | 10:00 | 11:15 | Inspected column reinforcement — approved
SAFETY
Toolbox talk | Working at height on scaffolds | Incidents / near misses |  | None
PPE check | All workers in boots & helmets
ISSUES / DELAYS / INSTRUCTIONS RECEIVED
1. Rain stopped work for 1.5 hours. 2. Client asked to move the kitchen window 600mm left — awaiting architect confirmation (RFI-007). 3. Vibrator out for repair, back tomorrow.
PLAN FOR TOMORROW
Pour lintel concrete over bedrooms 1–2 (weather permitting), continue blockwork bedrooms 3–4.
Site supervisor |  | Received by client / PM
Name: |  | Name:
Date: |  | Date:
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build — log daily progress with photos for free at https://nigeriabuildingcost.ng/construction-management-software-nigeria