## Non-conformance report
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Non-Conformance Report (NCR)
Records work that does not meet the drawings or specification, and how it was fixed
NCR no. | NCR-003
Date found | 2026-10-10
Raised by | Structural engineer
Location | Ring beam, rear elevation (gridline 4)
1. NON-CONFORMANCE
Concrete cover to ring beam reinforcement measured at 10–15mm on the outer face. Specification requires 25mm minimum. Two spacer blocks missing over a 3m length.
Classification | Major / Minor
Spec / drawing ref. | S-201 General notes, cl. 4.2
Work affected | Ring beam 3m length
Discovered by | Inspection before plastering
2. IMMEDIATE CONTAINMENT
Plastering on the rear elevation stopped. Area marked and photographed.
3. ROOT CAUSE
Spacer blocks not tied securely; dislodged when concrete was poured from height. No check of cover by the supervisor before the pour.
4. CORRECTIVE ACTION
Action | Detail | Due date
Repair | Apply 15mm polymer-modified repair mortar over affected length to reach 25mm cover | 2026-10-15
Prevent repeat | Concrete spacers tied at max 1m centres; supervisor checks cover on every pour (add to pre-pour checklist) | 2026-10-14
5. VERIFICATION & CLOSE-OUT
Verified by
Date verified
Cost of repair (₦) | 38000
Charged to | Contractor
Raised by | Contractor | Closed by
Name: | Name: | Name:
Date: | Date: | Date:
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build at https://nigeriabuildingcost.ng/construction-management-software-nigeria