## Plant & equipment
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Plant & Equipment Register
What you own, where it is, who has it, and what it is worth now
Company |  | Example Builders Ltd |  | Updated |  | 2026-10-13
Asset ID | Description | Location | Responsible | Purchased | Cost | Depr. / yr | Current value | Status
EQ-001 | Concrete mixer, 1-bag, diesel | Lugbe site | Site supervisor | 2024-02-10 | 1850000 | 20% | 860250 | In use
EQ-002 | Poker vibrator, petrol | Workshop | Storekeeper | 2024-02-10 | 420000 | 25% | 139125 | Under repair
EQ-003 | Generator 7.5kVA | Lugbe site | Site supervisor | 2023-06-01 | 1350000 | 20% | 441000 | In use
EQ-004 | Steel scaffolding set (100 frames) | Kubwa site | Foreman | 2022-11-15 | 3200000 | 10% | 1948444.4444 | In use
EQ-005 | Dumpy level & tripod | Office | Engineer | 2023-01-20 | 380000 | 15% | 167358.3333 | Available
EQ-006 | Wheelbarrows (×8) | Lugbe site | Foreman | 2025-08-01 | 280000 | 33% | 169120 | In use
|  |  |  | TOTAL | 7480000 |  | 3725297.7778
Formulas:
Current value = IF([Cost]="","",MAX(0,[Cost]*(1-[Depr. / yr]*YEARFRAC([Updated],TODAY()))))
Current value = IF([Description]="","",IF([Cost]="","",MAX(0,[Cost]*(1-[Depr. / yr]*YEARFRAC([Updated],TODAY())))))

## Maintenance requests
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Maintenance Request & Repair Log
Log every breakdown — repeat failures show what to replace
Req. no. | Asset ID | Date | Problem | Urgency | Assigned to | Cost | Fixed on | Status
MR-011 | EQ-002 | 2026-10-12 | Engine will not start; recoil starter broken | High | Mechanic (name) | 35000 |  | In progress
MR-010 | EQ-001 | 2026-09-22 | Drum bearing noisy | Medium | Mechanic (name) | 48000 | 2026-09-24 | Done
MR-009 | EQ-003 | 2026-09-02 | Routine service — oil, filters | Low | Generator technician | 28000 | 2026-09-02 | Done
[5 empty] | TOTAL | 111000
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build at https://nigeriabuildingcost.ng/construction-management-software-nigeria