## Snag list
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Punch List (Snag List)
Everything that must be fixed before handover — walk the building room by room
Project |  | 4-bedroom bungalow (example) | Location | Lugbe, Abuja
Client |  | Mr & Mrs Adeyemi (example) | Contractor | Example Builders Ltd
Inspection date |  | 2027-03-05 | Inspected by | Client, PM, contractor
# | Location | Defect / item | Responsible | Due | Fixed on | Status
1 | Living room | Hairline crack in plaster above main door | Plasterer | 2027-03-10 |  | Open
2 | Living room | Two floor tiles hollow-sounding near window | Tiler | 2027-03-10 | 2027-03-09 | Fixed
3 | Kitchen | Sink tap leaking at base | Plumber | 2027-03-08 | 2027-03-08 | Closed
4 | Master bedroom | Wardrobe wall paint patchy — needs extra coat | Painter | 2027-03-12 |  | Open
5 | Bedroom 2 | Window does not lock — handle misaligned | Aluminium installer | 2027-03-10 |  | In progress
6 | Bathroom 3 | Floor slopes away from drain — water ponds | Tiler | 2027-03-12 |  | Open
7 | Corridor | Socket outlet not working | Electrician | 2027-03-08 | 2027-03-08 | Closed
8 | External | Gutter joint dripping at rear | Roofer | 2027-03-12 |  | Open
Total items |  | 8
Open |  | 5
Fixed / closed |  | 3
"Fixed" = contractor says it is done. "Closed" = client/PM has checked and accepted it. Release retention only when every item is closed.
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build at https://nigeriabuildingcost.ng/construction-management-software-nigeria