## RFI form
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Request for Information (RFI)
Ask the architect, engineer or client to clarify a drawing or spec — in writing
RFI no. | RFI-007
Date | 2026-10-13
From | Example Builders Ltd (contractor)
To | Project architect
Drawing / spec ref. | A-102 Ground floor plan, Rev C
Reply needed by | 2026-10-16
QUESTION
Client has asked on site to move the kitchen window 600mm to the left. Drawing A-102 shows it centred on the sink wall. Please confirm the new position and whether the lintel length changes.
SUGGESTED SOLUTION (CONTRACTOR)
Move window 600mm left; extend lintel by 300mm each side as normal. Sink position unchanged. No cost impact if confirmed before Friday (blockwork reaches that wall on Monday).
IMPACT IF NOT ANSWERED IN TIME
Cost impact | None / TBC
Schedule impact | Blockwork on kitchen wall on hold from 19-Oct
RESPONSE
(Architect / engineer to write answer here)
Answered by | Received by contractor
Name: | Name:
Date: | Date:

## RFI log
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
RFI Log
Track every RFI until it is answered
RFI no. | Date sent | Subject | Sent to | Reply due | Answered | Status
RFI-005 | 2026-09-28 | Column C4 size differs between arch. and structural drawings | Structural engineer | 2026-10-01 | 2026-09-30 | Closed
RFI-006 | 2026-10-06 | Tile type for guest toilet not specified | Client | 2026-10-10 |  | Open
RFI-007 | 2026-10-13 | Kitchen window position change | Architect | 2026-10-16 |  | Open
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Track My Build at https://nigeriabuildingcost.ng/construction-management-software-nigeria