## RFP
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Request for Proposal (Invitation to Tender)
Send to contractors so every bid comes back in the same format
Issued by | Mr & Mrs Adeyemi (example)
RFP ref. | RFP-LUG-001
Date issued | 2026-10-13
Bids due | 2026-10-31
PROJECT BACKGROUND
We plan to build a 4-bedroom bungalow (approx. 165m²) on a fenced 15m × 30m plot in Lugbe, Abuja. Approved drawings and a Bill of Quantities are attached. Soil test shows normal bearing capacity.
GOALS
• Handover by 31 March 2027
• Total cost within ₦55–60 million including VAT
• Transparent monthly reporting with photos
SCOPE
Full construction from site clearance to handover as described in the attached BoQ and drawings. Fence, borehole and solar are NOT part of this tender.
WHAT YOUR PROPOSAL MUST INCLUDE
Item | Details required | Included? (Y/N)
Priced BoQ | Every line priced; do not change quantities — note any errors separately
Programme | Gantt chart or week-by-week plan
Payment schedule | Proposed stage payments (max 40% advance)
Company profile | Registration (CAC), 3 similar completed projects with photos and references
Key staff | Site supervisor and engineer names and COREN/NIOB registration
Insurance | Contractor's all-risk insurance details
Exclusions & assumptions | Anything you have not priced
HOW BIDS WILL BE EVALUATED
Criterion | What we look for | Weight
Price | Total and completeness of the priced BoQ | 40%
Experience | Similar projects completed, references | 25%
Programme | Realistic timeline and resources | 15%
Team | Qualified engineer and supervisor | 10%
Reporting | How progress and spending will be shared | 10%
| Total | 100%
SUBMISSION
Email PDF and Excel copies to: (your email) by 5pm on the due date. Site visits available Mon–Sat by appointment. Questions in writing by 24 Oct 2026; answers will be shared with all bidders.
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Quote Checker (check bids against market rates) at https://nigeriabuildingcost.ng/quote-checker