## Valuation
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Schedule of Values / Interim Valuation
Contract sum split by work section — % complete drives each payment
Valuation no. | 3 |  | Valuation date | 2026-10-31
Project | 4-bedroom bungalow (example) |  | Location | Lugbe, Abuja
Client | Mr & Mrs Adeyemi (example) |  | Contractor | Example Builders Ltd
Work section | Scheduled value | % complete | Work done to date | Previously certified | This valuation
Substructure | 9266000 | 100% | 9266000 | 9266000 | 0
Frame & walling | 12172000 | 100% | 12172000 | 10346000 | 1826000
Roofing & ceiling | 9321000 | 60% | 5592600 | 1864000 | 3728600
Doors & windows | 1454000 | 30% | 436200 | 0 | 436200
Finishes | 7845000 | 0% | 0 | 0 | 0
Services | 3328000 | 10% | 332800 | 0 | 332800
TOTAL | 43386000 |  | 27799600 | 21476000 | 6323600
|  | Gross value this valuation |  |  | 6323600
|  | Retention (%) |  |  | 5%
|  | Less retention |  |  | -316180
|  | Materials on site (unfixed) |  |  | 950000
|  | NET AMOUNT CERTIFIED |  |  | 6957420
Contract sum | 43386000
Overall % complete (%) | 64.08%
Contractor |  |  | Client's QS / Project Manager
Name: |  |  | Name:
Date: |  |  | Date:
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Interim Valuation Calculator at https://nigeriabuildingcost.ng/interim-valuation-calculator