## Variation order
NigeriaBuildingCost.ng · Free construction template — edit the blue cells, totals calculate automatically
Variation (Change) Order
Records an approved change to scope, cost and time
Variation no. |  | VO-004
Date raised |  | 2026-10-09
Project |  | 4-bedroom bungalow (example)
Location |  | Lugbe, Abuja
Client |  | Mr & Mrs Adeyemi (example)
Contractor |  | Example Builders Ltd
Requested by |  | Client
Original contract sum |  | 52400000
DESCRIPTION OF CHANGE
Client requested the boys' quarters roof to be changed from aluminium long-span to stone-coated tiles to match the main house, and an additional 2 external lights on the gate pillars.
REASON
Aesthetic upgrade requested by client after site visit on 07-Oct-2026. Not a design error.
COST OF CHANGE
# | Item | Qty | Unit | Rate | Amount
1 | Omit: 0.55mm aluminium roofing sheets (BQ) | -48 | m² | 15000 | -720000
2 | Add: stone-coated roof tiles incl. accessories | 48 | m² | 22000 | 1056000
3 | Add: extra purlins for stone-coated tiles | 30 | pieces | 4500 | 135000
4 | Add: external wall lights incl. wiring | 2 | nr | 16000 | 32000
|  |  |  | Net change | 503000
|  | Original contract sum |  |  | 52400000
|  | Previous approved variations |  |  | 1350000
|  | This variation |  |  | 503000
|  | REVISED CONTRACT SUM |  |  | 54253000
Time impact (days) |  | 4
Revised completion |  | 2027-04-18
Contractor |  | Client |  | Consultant / PM
Name: |  | Name: |  | Name:
Date: |  | Date: |  | Date:
Free template from NigeriaBuildingCost.ng. Rates are indicative (Oct 2026) — check current prices in your location before relying on any figure. Faster option: use the free Quotation Generator at https://nigeriabuildingcost.ng/quotation